## Sheet1
Enhancement/Bug Description | Request Date | Priority | Requester | Request Type | Approved By Entire Team? | Fixed? | Assigned To | Fixed By | Date Fixed | Notes
Find new pictures for website | 2015-03-01 | Low | All | Web | Y | N | Naveen |  |  | Maybe find pictures for main page similar to ones in PulseBox page.
Complete load process | 2015-03-11 | Med | Abdul | Database | Y | N | Naveen |  |  | Handle inserts that come in from customers via text file. Pretty much done, but need to put finishing touches on it.
Complete update process | 2015-03-11 | Med | Abdul | Database | Y | N | Naveen |  |  | Handle changes (updates/deletes) that come in from customer via file.
Come up with design for left side of PulseBox page | 2014-03-11 | Low | Abdul | Database | N | N | Naveen |  |  | Need few ore buttons/informational tabs (home, models, pricing, versions, FAQ,videos, arch diagrams, white papers, etc) on left side of PulseBox page. Naveen sent design 3/25 for us to review.
PulseBox webpage has dot in corner plus change "Pulse Box is your answer" to "PulseBox is your answer" | 2015-03-11 | Low | Abdul | Web | N | N | Alex | Alex | 2015-03-28 | Corner of the pictures has little dot that needs to be removed. Plus change "Pulse Box is your answer" to "PulseBox is your answer" (PulseBox is one word). The dot issue is resolved, but "Pulse Box is your answer" needs to be changed to "PulseBox is your answer" so keeping this item open.
When there is no data/pulses available for the selected criteria of a report, display informational message instead of empty graph. | 2015-03-11 | Med | Abdul | Web | N | N | Alex |  |  | Right now user gets an empty graph. Would be nice to display something like "No Data Available for Selected Criteria" instead. We are doing this already for Events - when there is no data we get message "No Events for the range of dates provided"!
Participation report x-axis (dates) still wrong order | 2015-03-11 | High | Abdul | Web/Proc | N | N | Alex/Dave |  |  | For aebadi2 (emp_id=6029), I choose 3 depts (HR, IT, SALES) and entire 2014 as date range. Graph x-axis out of order! Order is fine if you choose one dept, but anytime more than one is chosen order is wrong.. Plsql is ording by Date datatype col. Results showing correctly in sqlplus. Alex can put Participation report in separate graphs and that should solve this issue.
Design & document input process | 2015-03-25 | High | Abdul | Design | Y | N | Abdul/Naveen |  |  | Before Alex can implement this in our demo, need to come up with design and documentation for how the input section should look and feel like.
Participation Report enhancement | 2015-03-25 | Low | Abdul | web | N | N | Alex/Dave |  |  | Would be nice to have y-axis of participation report as a percentage instead of a decimal and label it "Percentage". Low priority, so if it's too much work we can save it for after demo. Dave completed his part and looks good. I think only thing we still need to do is change the label of Y axis to "Percentage" from "Pulse".
Both"Participation Report By Department" and "Attrition Report by Department" should be changed to just "Participation Report" and "Attrition Report" | 2015-03-25 | Low | Abdul | Web | N | N | Alex |  |  | Since we can aggregate the label should be changed and "by Department" should be removed from label in both reports.
Add default null to every start/end date for every procedure.. | 2015-03-25 | Med | All | Procedure | Y | N | Dave |  |  | Add default null to every start/end date for every procedure to fix empty/null situation. Dave completed his part in proc. However, when leaving dates empty we in demo we are still getting error.
Put together expense spreadsheet | 2015-03-30 | Low | All | Expense | Y | N | Naveen |  |  | Get list of all expenses for team and update spreadsheet.
Validate user input | 2015-03-26 | Med | All | Web | Y | N | Alex |  |  | Handle bad data such as 15-25-2015 as date. Related to "add default null", but this will be from web side.
DD will investigate using Calendar table in procs to provide standard width for x-axis dates | 2015-03-26 | Low | Dave | Procedure | Y | N | Dave |  |  | DD will investigate using Calendar table in procs to provide standard width for x-axis dates. Adding this per DD. Very low priority.
Add more data | 2015-03-01 | Med | Alex | Database | Y | N | Naveen/Abdul |  |  | Need to utilize new automated load process to load more recent data. Plus make sure data makes reports useful.
Combine EMPLOYEE data and login data in SQL Server | 2015-03-01 | Low | All | Web | Y | N | Alex |  |  | Migrate login information from SQL Server db to Oracle. Ideally, would like to just be on Oracle.
Start user input from web | 2015-03-10 | Med | All | Web | Y | N | Alex |  |  | After reporting for demo is complete start the user input process. In the user input screen(s) user should be allowed to answer standard 10 questions, but most importantly he/she should be able to enter free text input after answering 2-3 other questions with a rating. We should turn this free text into a question based on the 2-3 questions they answer so we can enter it into our db!
When graph has single point it shows as empty! | 2015-03-11 | Med | Abdul | Web | N | N | Alex/Dave |  |  | We need two points to draw a line/graph. When we hav a single point for the time period selected the graph shows empty. Maybe we should display bar graph or something when there is one data point.
X-axis (date values) could be misleading. | 2015-03-11 | Med | Abdul | Web | N | N | Alex/Dave |  |  | I ran a company pulse report for Jan-1-14 to Feb-28-14 for aebadi2. There were pulses for 5 different dates: Jan 1, Feb 2, Feb 9, Feb 10, Feb 23. These dates are spread, but graph made it look like they were next to each other.
Add Question Category as new tab | 2015-03-12 | Low | All | Web/Proc | Y | N | Alex/Dave |  |  | Future enhancement to add a new tab which has question category filter.
PulseBox Mobile | 2015-03-13 | Low | All | All | Y | N | All |  |  | After our demo is tested and ready for prime time we should come up with an app for PulseBox to make it mobile friendly. Then, sky will really be our limit!
Remember user selections | 2015-03-25 | Low | Dave | web | Y | N | Alex |  |  | If possible, somehow remember selections a user makes when running a report, so incase they want to go back and make a slight modification (ex. One less dept) and run it again. Low priorioty so after demo is fine also.
Revisit and improve look and feel of entire website | 2015-03-25 | Med | Alex | Web/Design | Y | N | All |  |  | Need to revisit look and feel of our entire website to make sure we are sending the right message to our customers. The website should have nice flow and provide just the right amount of information to make our potential customers aware of our product!
Attrition report wrong graph? | 2015-03-29 | Med | Abdul | Web/Proc | N | N | Alex/Dave |  |  | I ran attrition report as aebadi2 (emp_id 6029) and selected all departments and entire 2014 as date range and aggregate with all 5 charts select (avg,min,max.stddev,variance). Problem is same exact chart shows for all of them. Is this even possible?
Add forecasting tab | 2015-03-29 | Low | Abdul | Web | N | N | All |  |  | Add a tab in the reporting section that will provide a report on futureforecasting capabilties of PulseBox.
Document load/update process | 2015-03-30 | Low | Abdul | Document | N | N | Naveen |  |  | Once load/update process is completely test/ready then document it for our own sake.
Create admin user | 2015-03-30 | Low | Abdul | Web | N | N | Alex |  |  | Create admin user for each company w/ ability to update certain fields in industry, location, department, company, and employee tables. These are all tables required in initial load process.
Industry report aggregate minor problem | 2015-03-30 | Med | Abdul | Web | N | N | Alex |  |  | When I run industry report as aebadi or aebadi2, select entire 2014 as date range, all industries, DTM Data company, Aggregate, and AVG and MAX charts the industry graph is fine and only shows AVG and MAX. However, the company graph shows all AVG,MIN,MAX,STDDEV,VARIANCE even though I chose only 2!
All Button | 2015-03-10 | High | Dave/Abdul | Web | N | Y | Alex | Alex | 2015-03-24 | Need to add and "All" button/option to all our demo reports where it selects all fields (depts, locs, industries, whatever) so user doesn't have to click each of them separately.
Fix "Submmit" button in demo page | 2015-03-01 | High | Abdul | Web | Y | Y | Alex | Alex | 2015-03-12 | Spelling mistake… replace "Submmit" with "Submit" in demo (after you login). Fix: replaced "Submmit" with "Create Charts".
Attrition report issue | 2015-03-10 | Med | Abdul | Web/Stored Proc | Y | Y | Alex/Dave | All | 2015-03-12 | Attrition report needs to have a dropdown for Question Category to allow user to pick a category that they can tie to attrition. Or, for demo we can just hard-code the "Attrition" category behind the scenes. If this is the case and has been done in proc then this report is OK/fixed. After further testing, I think we are good as is! I verified that the only pulses are coming back for this report are for question_category called "Attrition" which is exactly what we want! :) Fix: attrition report good as is as it's bringing back pulses for question category "attrition". We will add future enancement for question category.
Industry report needs current company added | 2015-03-10 | High | Abdul | Web | Y | Y | Alex | Alex | 2015-03-13 | The Industry report currently lists a set of industries that the user can pick which is fine. In that list it should also allow the user to choose the current company as an option to choose in addition to industries. Fix: Alex added current company name as option.
Participation report displaying wrong graph | 2015-03-10 | High | Abdul | Web | N | Y | All |  | 2015-03-25 | After running one report successfully for Participation report the second one displays the exact same thing! After further tests found out you have to clear your browsing history and log back in to make it work. Need to do more analysis on this and find a fix. More tests showed that this behavior is only with Internet Explorer and Chrome is fine. Ran lots of tests on 3/25 and didn't see this issue so calling it fixed (Abdul).
Get "Contact Us" email working | 2015-03-01 | Med | All | Web | Y | Y | Alex | Alex | 2015-03-12 | Make sure when someone goes to our website and clicks on "Contact Us" that we get email at info@dtmdata.com. Fixed and tested!
Add Employee or Manager option to login | 2015-03-10 | Med | Abdul | Web | Y | Y | Alex | Alex | 2015-03-24 | When user logs into demo, determin if he/she is an employee (no directs) or a manager. If an employee then he is only allowed to enter pulse and no viewing of reports! If he/she is a manager then he/she can enter pulse as well as run reports! You can figure out if somone is a manager by looking at other employees and if anyone in that company has this emp_id in their manager_id column then this one is a manager. If not then he is an employee only. Fixed on 3/24.
Industry report displaying wrong data. | 2015-03-11 | High | Abdul | Procedure | N | Y | Dave | Dave | 2015-03-24 | I ran Industry report using aebadi (emp_id=6005) for Software industry only. This is industry_id 1003. The companies in this industry are: 3002, 3008, 3009. So, this report should only be displaying pulses for these companies, but it looks like it is not. There were no pulses at all for these on Jan-3-2014 but the report shows pulses! Works for Abdul as of 17Mar2015; DD still to review/test plsql logic. After further testing on 3/17 looks like graph/data is good. Keeping item open per DD. Ran report again on 3/25 and works well so closing it!
Improve "Contact Us" page | 2015-03-12 | Med | All | Web | Y | Y | Alex | Alex | 2015-03-12 | Make improvements such as: * for required fields, better messaging, etc. Fix: did these plus more!
Industry report | 2015-03-17 | Med | DD | web | n | Y | Alex | Alex | 2015-03-24 | When navigating back from a resulting graph page, DTMData changes to Medium Company. And also only single chart shows up, for Company. Even though not checked. Alex says known issue and will fix. I (Abdul) ran tests on 3/25 and issue not there.
Contact Us page | 2015-03-17 | Low | DD | web | n | Y | Alex | Alex | 2015-03-26 | In bottom band which contaibns Copyright info, way off to the right I see the top of a "C"…bottom of it pushed into White below the gray.
Spelling fixes on website | 2015-03-25 | Med | Abdul | web | Y | Y | Alex | Alex | 2015-03-26 | Couple of spelling mistakes: 1) Industry report - "Please select the indistries" to "industries" 2) "Aggreagate" to "Aggregate" in all reports
Participation Report small display issue | 2015-03-25 | Med | Abdul | Web | N | Y | Alex | Alex | 2015-03-26 | When you click on Participation report you see a simicolon ";" right below the "Logout". Please remove this semicolon.
Move "Demo" button from our website to after login | 2015-03-25 | Med | Alex | Web | Y | Y | Alex | Alex | 2015-03-26 | Only after logging in should someone have access to our demo.
Aggregate Button | 2015-03-10 | High | Dave/Abdul | Web | N | Y | Alex | Alex | 2015-03-28 | Need to add and "Aggregate" button/option to all our demo reports where it displays the graph as an aggregate of all chosen fields (depts, locs, industries, whatever).
Modify "Copyright 2014 - DTM Data…" to "Copyright 2015 - DTM Data, LLC" in website | 2015-03-11 | Low | Abdul | Web | N | Y | Alex | Alex | 2015-03-28 | Our company name is officially reserved - DTM Data, LLC. Plus update the year to 2015.
Bigger Graphs? | 2015-03-11 | Low | Abdul | Web | N | Y | Alex | Alex | 2015-03-28 | Any chance we can make graph bigger and bolder so it stands out and takes up more room? Would look nice!
Label left side of graph | 2015-03-25 | Med | Naveen | web | Y | Y | Alex | Alex | 2015-03-28 | Label the left side (y axis) of graphs "Pulse". Currently, it is empty.
Enhance labeling for AVG, MIN, MAX, STDDEV, VARIANCE | 2015-03-25 | Low | Alex | Procedure | Y | Y | Alex | Alex | 2015-03-28 | Improve labels for AVG, MIN, MAX, STDDEV, VARIANCE. So, maybe more descriptive labels like AVG Pulse etc?
Add "Aggregate" option for Participation Report | 2015-03-25 | Med | Abdul | Web | N | Y | Alex | Alex | 2015-03-28 | Add "Aggregate" option to Participation report also just like others.
Calendar messed up in Chrome | 2015-03-10 | Low | Abdul | Web | N | Y | All |  | 2015-03-29 | Sometimes calendar doesn't display correctly or allow me to choose dates! Dave things could be a driver issue. Works fine when I use Internet Explorer. Calendar looked much better for my (Abdul) testing on 3/25/2015! More testing on 3/29/2015 shows I didn't have any weird issues with Chrome so closing this one (Abdul).
Overlay graphs | 2015-03-10 | Low | Dave/Abdul | Web | N | Y | Alex | Alex | 2015-03-29 | Figure out a good way to overlay graphs rather than separate graphs for things like locations, departments, industries, etc. We discussed that maybe limiting the user to only one (AVG, MIN, MAX, STDDEV, VARIANCE) if they have chosen separate departments/locations/industries to graph. Still need to discuss this further. If too much then we leave it as is for POC. Closing it as with further testing realizing sometimes overlay is good and sometimes separate so we'll take it case by case (Abdul).
Display lists in alphebetical order | 2015-03-25 | Med | Abdul | Procedure | Y | Y | Dave | Dave | 2015-03-29 | Currently lists such as depts, locs, industries are not in any order. Would like to display them in alphebetical going forward. Basically, all sp_get* procs.
Industry report issue | 2015-03-25 | High | Abdul | Web/Proc | N | Y | Alex/Dave | Dave | 2015-03-30 | For user aebadi (same issue for aebadi2), I ran Industry report and chose all industries as well as DTM Data company. I only got two graphs - one for DTM Data and one for Software Industry. There should have been more graphs for other industries. Looks like it may only be displaying data in the industries the current company is in. DD... double check WHERE clause to make sure it's done right. DD thinks the "WHERE 1=1 and A.company_id = v_IN_company_id" in the proc might be causing it to bring back only industries for this company. Report should: it should be pulses for all companies in that industry whichever industry id is passed doesnt matter if the current company is part of that industry or not. Fixed by dd and confirmed by axe.